| Region and Area: | North West - South |  | Contact name(s): | Jo Harris (Comms) Katherine Causer (Catchment Coorinator) |  | Date: | September/December 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site / issue name: | WFD – River Irwell Pilot |  |  |  |  |  |  |
| Business objective(s): | To explore better ways of engaging with people and organisations to help deliver the Water Framework Directive. The pilot will test approaches to engagement. What we learn will help inform how we deliver healthier water environments in the future. |  |  |  |  |  |  |
| Engagement objective(s): | 1 To identify all interested parties and get agreement for their input in to the pilot 2 Ensure stakeholders understand the aims of the pilot and all relevant evidence is gathered from local people 3 To keep key partners and interested public informed about progress of the pilot 4 Media coverage is fair and accurate |  |  |  |  |  |  |
| Summary of engagement work to date: | Phase 1. Set up workshops/meetings to build relationships/get buy in from partners – agree direction of the pilot Phase 2. Newsletters/websites/media – Keeping partners informed and local communities aware of actions Phase 3 Ongoing engagement – keeping people informed as to progress on improvements/ways of working agreements etc |  |  |  |  |  |  |
| Relevant engagement objective | Indicators / success criteria How we’ll know the engagement has been successful | Evidence to be used How and where we’ll get the evidence to test the indicators |  |  | Conclusions3 Evidence showing that the objective has been met |  |  |
| Engagement Objective 1 To identify all interested parties and get agreement for their input in to the pilot | All partners and interests groups agree on the representatives to be included as part of the pilot. Format of the pilot is agreed by all | Workshop with partners organisations Evaluation Sign up to group |  |  | Hosted workshop with wide range of partner organisations to explain aims of the pilot. Target stakeholders Response to questionnaire - Everyone thought that the workshop was the best way of gathering and giving information. There was a comment on the need to involve and share information with a wider audience. Verbal feedback was positive with some actions for improvement identified. Evaluation charts showed all thought that the workshop had helped get the group off to a good start. 7 of the target SHs signed up to being in the steering group. Most of the others wanted to be kept informed and to be involved in other way. |  |  |
| Engagement Objective 2 Ensure stakeholders understand the aims of the pilot and all relevant evidence is gathered from local people | EA seen as key partner, but not lead role – to ensure the pilot is recognised as collective. Each partner organisation or local group to agree on how and when progress is shared. | Qualititative phone questionnaire (tbd Jan 12) |  |  |  |  |  |
| Engagement Objective 3 To keep key partners and interested public informed about progress of the pilot | Stakeholders feel informed and are able to discuss the pilot and outcomes with others. | Qualititative phone questionnaire (tbd Jan 12) |  |  |  |  |  |