Irwell Pilot Communications action plan and engagement log – Draft

Background

Communications objectives

To engage with partners, stakeholders and the public to

- raise awareness of the issues the Irwell catchment faces.

- identify the best communications methods for the relevant audiences.

- identify actions to improve water quality.

- raise awareness of the benefits of integrated catchment management.

- enable interactive participation in the pilot.

Possible methods of engaging Stakeholders could be

- Engagement through other organisations (sector led, chemicals NW, NFU etc)

- 121 meetings

- Workshops bringing groups of Stakeholders together

- Drop in sessions (industrial sites etc)

Approach to public facing communications

As the project proceeds, we will identify work that is already happening that will contribute towards achieving the aims of the pilot. It would be beneficial as these opportunities present themselves, to encourage the relevant organisations to promote this emphasizing the links it has to improving the wider water environment in the catchment.

Further down the line, through engagement we will have a plan of actions that, through working with others, we’ll deliver to improve the water environment.  When this plan is further developed we can plan relevant communications about individual projects in order to promote the aims of the pilot and engage communities with improving the catchment.

We will seek advice from our stakeholders about the best way to engage the public and where possible, do this through the stakeholders.

Evaluation

Nationally lead

Engagement Action Plan

| Date | Activity | Who’s leading? | Who’s involved | Output |
| --- | --- | --- | --- | --- |
| May | Collating stakeholder information from internal staff about who they engage with through their work | Katherine | All relevant staff | Comprehensive Stakeholder list. |
| May | 121 meetings with | Gordon | Other organisations:-Salford, Bolton, Groundwork, Healthy Waterways Trust, Keep Britain | Awareness raising around pilot and getting their thoughts. Initial scoping conversations. |
| May | 121 meetings with Salford friendly anglers, Irwell rivers trust | Kevin Nash/ Katherine |  | Awareness raising around pilot and getting their thoughts. Initial scoping conversations. Gather feedback on our approach to the project. |
| June | Internal Stakeholder workshop | Katherine | Katherine & Jo Area & Regional team members Matthew Schofield Irwell Rivers Trust | Activity mapping, ‘Big Ideas’ for additional activities, key stakeholder ID |
| June | On-going stakeholder communications | Katherine | LA’s, Salford Friendly Anglers, Moston Brook Project, IRT | Awareness raising, information gathering, Ideas sharing |
| July | Meeting/Workshop | Paul Roots/Katherine | NENW IF | Scope opportunities to develop ways of working with grassroots organisations / local people to identify investment needs. |
| July | Meeting | Gordon | GW, BTCV, RRF, LWT, KBT | Scope possibilities for additional action using ‘trusted’ 3rd sector organisations |

| Date | Activity | Who’s leading? | Who’s involved | Output |
| --- | --- | --- | --- | --- |
| July | Workshop | Katherine | LA’s RRF, LWT, BTCV, Groundwork | Determine activities occurring in the Irwell Pilot catchment and find out what the barriers & big issues are. Networking opportunity. |
| August | 121 meetings (mop-up from workshop) | Katherine | Various | Determine activities occurring in the Irwell Pilot catchment and find out what the barriers & big issues are |
| August | Follow-up meeting | Gordon/Katherine | GW, BTCV, RRF, LWT, KBT | Ideas to be presented by stakeholder on activities they can carryout to contribute to WFD outcomes |

| Date | Activity | Who’s leading? | Who’s involved | Output |
| --- | --- | --- | --- | --- |
| July | Local community stakeholder engagement workshop | Katherine | Internal/External stakeholders | Information sharing, activity mapping, ID aspirations, sharing information, developing ideas for additional activities, identifying barriers and enablers to delivery |
| July | Local Authority engagement | Gordon/Katherine/Mark Chadwick | All relevant LA’s | Awareness raising, scope possibilities for additional action, better ways of working with LA’s |
| Aug | Review of regulatory activity and relevant stakeholders | Gordon | AMT/Team Leader core group | Scope possibilities for additional action, better ways of working |
| Aug | Review of engagement with Peel & UU | AMT | AMT/Team Leader core group | Scope possibilities for additional action, better ways of working |
| Sept | Meeting | External stakeholder to be identified | Relevant stakeholders | Development Irwell Pilot Stakeholder Group |
| March | Development of an Irwell Catchment Action Group | Katherine and External Stakeholder | Relevant stakeholders | Development of Catchment Action Plan |